## Version History
Product Name (Client Name) | TechHub
Prepared By
Version No | Version 1.0
| Version 2.0 | Updated with execution results

## Test Scenarios
Project Name | TechHub (Frontend)
Client | TechHub
Reference Document | Application UI / Screenshots
Created By
Creation Date | March 2026
Approval Date | DD-MM-YYYY
Test Scenario ID | Reference | Test Scenario Description | Priority | Number of Test Cases
(TS_001) Home Page | UI | Validate the working of Home Page functionality | P0 | 10
(TS_002) Image Slider | UI | Validate the working of Image Slider on Home Page | P0 | 8
(TS_003) CTA Buttons | UI | Validate 'Start Learning Now' and 'Watch Demo' buttons on Home Page | P0 | 6
(TS_004) Navigation Bar | UI | Validate the working of Navigation Bar across all pages | P0 | 10
(TS_005) Explore Menu | UI | Validate the working of Explore dropdown menu and all categories | P0 | 12
(TS_006) Search Bar | UI | Validate the working of Search Bar functionality | P1 | 10
(TS_007) Signup Page | UI | Validate the working of Signup page and form field validations | P0 | 18
(TS_008) Login Page | UI | Validate the working of Login page and form field validations | P0 | 16
(TS_009) Social Login | UI | Validate the display and working of Social Login buttons | P1 | 6
(TS_010) Contact Page | UI | Validate the working of Contact page functionality | P2 | 8
(TS_011) Page Navigation | UI | Validate page navigation and URL routing between all pages | P1 | 8
(TS_012) UI Consistency | UI | Validate UI consistency and layout across all pages | P2 | 8
TOTAL |  |  |  | 120

## Home Page
Test Case ID | Test Scenario | Test Case Title | Pre-requisites | Test Steps | Test Data | Expected Result (ER) | Actual Result | Priority | Result | Comments
<< Test Scenarios
TC_HP_001 | (TS_001) Home Page | Validate TechHub Home page loads successfully | Open the URL in Chrome | 1. Open the application URL in Chrome 2. Observe the page (Validate ER-1) | Not Applicable | 1. Home page should load fully. Logo, navbar, hero section, slider, and CTA buttons should all be visible. | 1. Home page loaded fully. All elements visible including logo, navbar, hero section, slider, and CTA buttons. | P0 | PASS
TC_HP_002 | (TS_001) Home Page | Validate TechHub logo is visible on the Home page | Open the Home page | 1. Open the Home page 2. Look at the top-left of the navbar (Validate ER-1) | Not Applicable | 1. TechHub logo should be clearly visible in the top-left corner of the navbar. | 1. TechHub logo is clearly visible in the top-left corner of the navbar. | P0 | PASS
TC_HP_003 | (TS_001) Home Page | Validate hero heading text is displayed correctly | Open the Home page | 1. Open the Home page 2. View the left side of the hero section (Validate ER-1) | Not Applicable | 1. Heading 'Master IoT & Hardware Development in Weeks, Not Years' should be displayed. | 1. Heading 'Master IoT & Hardware Development in Weeks, Not Years' is displayed correctly. | P0 | PASS
TC_HP_004 | (TS_001) Home Page | Validate badge text 'Empowering 15,000+ Tech Innovators Worldwide' is visible | Open the Home page | 1. Open the Home page 2. Look below the navbar for the badge text (Validate ER-1) | Not Applicable | 1. The badge 'Empowering 15,000+ Tech Innovators Worldwide' should be visible. | 1. The badge text is visible below the navbar as expected. | P1 | PASS
TC_HP_005 | (TS_001) Home Page | Validate description paragraph is displayed below the heading | Open the Home page | 1. Open the Home page 2. View paragraph text below the main heading (Validate ER-1) | Not Applicable | 1. The description paragraph should be visible and readable. | 1. Description paragraph is visible and readable below the main heading. | P1 | PASS
TC_HP_006 | (TS_001) Home Page | Validate the Home page can be scrolled up and down | Open the Home page | 1. Open the Home page 2. Scroll down 3. Scroll back up (Validate ER-1) | Not Applicable | 1. Page should scroll smoothly in both directions without any layout breaking. | 1. Page scrolled smoothly in both directions without any layout issues. | P1 | PASS
TC_HP_007 | (TS_001) Home Page | Validate the Home page UI layout and alignment | Open the Home page | 1. Open the Home page 2. Review overall layout, font, color, and alignment (Validate ER-1) | Not Applicable | 1. All elements should be properly aligned. No overlapping text or broken layout. | 1. All elements are properly aligned. No overlapping or broken layout observed. | P2 | PASS
TC_HP_008 | (TS_001) Home Page | Validate the Home page in Microsoft Edge browser | Open in Edge | 1. Open the URL in Microsoft Edge 2. View the Home page (Validate ER-1) | Not Applicable | 1. Home page should display correctly in Edge with no visual differences from Chrome. | 1. Home page displays correctly in Edge. No visual differences from Chrome observed. | P2 | PASS
TC_HP_009 | (TS_001) Home Page | Validate the browser tab title on the Home page | Open the Home page | 1. Open the Home page 2. Check the browser tab text (Validate ER-1) | Not Applicable | 1. Browser tab should display a proper title related to TechHub, not just 'React App'. | 1. Browser tab is showing 'React App' on all pages instead of a page-specific title. | P3 | FAIL | TECHHUB-BUG-001
TC_HP_010 | (TS_001) Home Page | Validate the Home page does not show any console errors | Open the Home page | 1. Open the Home page 2. Press F12 to open DevTools 3. Check Console tab (Validate ER-1) | Not Applicable | 1. No red error messages should appear in the browser console on page load. | 1. No console errors observed on the Home page load. | P2 | PASS

## Image Slider
Test Case ID | Test Scenario | Test Case Title | Pre-requisites | Test Steps | Test Data | Expected Result (ER) | Actual Result | Priority | Result | Comments
<< Test Scenarios
TC_IS_001 | (TS_002) Image Slider | Validate image slider is visible on the Home page | Open the Home page | 1. Open the Home page 2. View right side of hero section (Validate ER-1) | Not Applicable | 1. A large image should be visible on the right side with left and right arrow buttons. | 1. Image slider is visible on the right side of the hero section with both arrow buttons. | P0 | PASS
TC_IS_002 | (TS_002) Image Slider | Validate clicking the right arrow changes the image to next slide | Open the Home page | 1. Open the Home page 2. Note the current image 3. Click right arrow (>) (Validate ER-1) | Not Applicable | 1. The image should change to the next slide when the right arrow is clicked. | 1. Image changed to the next slide on clicking the right arrow. | P0 | PASS
TC_IS_003 | (TS_002) Image Slider | Validate clicking the left arrow changes the image to previous slide | On slide 2 | 1. Advance to slide 2 2. Click left arrow (<) (Validate ER-1) | Not Applicable | 1. The image should return to the previous slide when the left arrow is clicked. | 1. Image returned to the previous slide on clicking the left arrow. | P0 | PASS
TC_IS_004 | (TS_002) Image Slider | Validate dot indicators are visible below the slider | Open the Home page | 1. Open the Home page 2. Look at the bottom of the slider (Validate ER-1) | Not Applicable | 1. Dot indicators (pagination bullets) should be visible at the bottom of the slider. | 1. Four dot indicators are visible at the bottom of the image slider. | P1 | PASS
TC_IS_005 | (TS_002) Image Slider | Validate clicking a dot indicator navigates to the corresponding slide | Open the Home page | 1. Open the Home page 2. Click on the 3rd dot indicator (Validate ER-1) | Not Applicable | 1. The slider should navigate to the 3rd slide when the 3rd dot is clicked. | 1. Clicking the 3rd dot navigated the slider to the 3rd slide correctly. | P1 | PASS
TC_IS_006 | (TS_002) Image Slider | Validate all images in the slider load without broken icons | Open the Home page | 1. Click through all slides using the right arrow 2. Check each image (Validate ER-1) | Not Applicable | 1. All images in the slider should load fully. No broken image icons should appear. | 1. All slider images loaded fully. No broken image icons observed. | P0 | PASS
TC_IS_007 | (TS_002) Image Slider | Validate slider arrow buttons respond on hover | Open the Home page | 1. Hover the mouse over the left and right arrow buttons (Validate ER-1) | Not Applicable | 1. Arrow buttons should change appearance on hover indicating they are clickable. | 1. Arrow buttons showed visual change on hover. Pointer cursor displayed correctly. | P2 | PASS
TC_IS_008 | (TS_002) Image Slider | Validate the slider does not break the page layout | Open the Home page | 1. Click through all slider images 2. Check page layout after each click (Validate ER-1) | Not Applicable | 1. Page layout should remain stable while navigating through slider images. | 1. Page layout remained stable and consistent throughout all slider navigation. | P1 | PASS

## CTA Buttons
Test Case ID | Test Scenario | Test Case Title | Pre-requisites | Test Steps | Test Data | Expected Result (ER) | Actual Result | Priority | Result | Comments
<< Test Scenarios
TC_CTA_001 | (TS_003) CTA Buttons | Validate 'Start Learning Now' button is visible on the Home page | Open the Home page | 1. Open the Home page 2. View the hero section (Validate ER-1) | Not Applicable | 1. The 'Start Learning Now' button with right arrow icon should be visible. | 1. 'Start Learning Now' button with arrow icon is clearly visible in the hero section. | P0 | PASS
TC_CTA_002 | (TS_003) CTA Buttons | Validate 'Start Learning Now' button is clickable | Open the Home page | 1. Open the Home page 2. Click on the 'Start Learning Now' button (Validate ER-1) | Not Applicable | 1. The button should respond to the click and navigate or perform an action. | 1. Button responded to click. Navigation action was triggered. | P0 | PASS
TC_CTA_003 | (TS_003) CTA Buttons | Validate 'Watch Demo' button is visible on the Home page | Open the Home page | 1. Open the Home page 2. View the hero section beside 'Start Learning Now' (Validate ER-1) | Not Applicable | 1. The 'Watch Demo' button with a play icon should be visible next to 'Start Learning Now'. | 1. 'Watch Demo' button with play icon is visible next to 'Start Learning Now' button. | P0 | PASS
TC_CTA_004 | (TS_003) CTA Buttons | Validate 'Watch Demo' button is clickable | Open the Home page | 1. Open the Home page 2. Click on the 'Watch Demo' button (Validate ER-1) | Not Applicable | 1. The button should respond to click and either play a demo or navigate to a page. | 1. Button responded to click. Action was triggered on click. | P1 | PASS
TC_CTA_005 | (TS_003) CTA Buttons | Validate both CTA buttons are visible side by side | Open the Home page | 1. Open the Home page 2. View the hero section layout (Validate ER-1) | Not Applicable | 1. Both buttons should appear side by side with proper spacing. | 1. Both buttons appear side by side with consistent spacing in the hero section. | P1 | PASS
TC_CTA_006 | (TS_003) CTA Buttons | Validate CTA buttons have correct hover effect | Open the Home page | 1. Hover the mouse over each CTA button (Validate ER-1) | Not Applicable | 1. Both buttons should show a visual change on hover. | 1. Both buttons showed color and cursor change on hover as expected. | P2 | PASS

## Navigation Bar
Test Case ID | Test Scenario | Test Case Title | Pre-requisites | Test Steps | Test Data | Expected Result (ER) | Actual Result | Priority | Result | Comments
<< Test Scenarios
TC_NB_001 | (TS_004) Navigation Bar | Validate the navigation bar is visible on the Home page | Open the Home page | 1. Open the Home page 2. View the top of the page (Validate ER-1) | Not Applicable | 1. Navbar should be visible with logo, Explore, Search bar, Contact, Login, Signup. | 1. Navbar is visible with all expected elements: logo, Explore, Search bar, Contact, Login, Signup. | P0 | PASS
TC_NB_002 | (TS_004) Navigation Bar | Validate the navigation bar is visible on all pages | Open the application | 1. Check navbar on Home, Login, Signup, Contact pages (Validate ER-1) | Not Applicable | 1. Navbar should be consistently visible across all pages. | 1. Navbar is consistently visible across all pages of the application. | P0 | PASS
TC_NB_003 | (TS_004) Navigation Bar | Validate clicking Login button navigates to Login page | Open the Home page | 1. Open Home page 2. Click 'Login' in navbar (Validate ER-1) | Not Applicable | 1. User should be navigated to Login page at /login. | 1. User is navigated to the Login page at URL /login. | P0 | PASS
TC_NB_004 | (TS_004) Navigation Bar | Validate clicking Signup button navigates to Signup page | Open the Home page | 1. Open Home page 2. Click 'Signup' in navbar (Validate ER-1) | Not Applicable | 1. User should be navigated to Signup page at /signup. | 1. User is navigated to the Signup page at URL /signup. | P0 | PASS
TC_NB_005 | (TS_004) Navigation Bar | Validate clicking Contact link navigates to Contact page | Open the Home page | 1. Open Home page 2. Click 'Contact' in navbar (Validate ER-1) | Not Applicable | 1. User should be navigated to Contact page at /contact. | 1. User is navigated to the Contact page at URL /contact. | P1 | PASS
TC_NB_006 | (TS_004) Navigation Bar | Validate clicking TechHub logo navigates back to Home page | Open the Login page | 1. Open /login 2. Click TechHub logo in navbar (Validate ER-1) | Not Applicable | 1. User should be navigated back to the Home page. | 1. Clicking the logo navigated back to the Home page as expected. | P1 | PASS
TC_NB_007 | (TS_004) Navigation Bar | Validate the Search bar accepts text input | Open the Home page | 1. Click on the Search bar 2. Type 'Arduino' (Validate ER-1) | Search text: Arduino | 1. The typed text 'Arduino' should appear in the search bar. | 1. Text 'Arduino' appeared in the search bar on typing. | P1 | PASS
TC_NB_008 | (TS_004) Navigation Bar | Validate the Search bar placeholder text is correct | Open the Home page | 1. View the Search bar without clicking it (Validate ER-1) | Not Applicable | 1. Placeholder text 'Search IoT, Hardware, Projects...' should be visible. | 1. Placeholder text 'Search IoT, Hardware, Projects...' is visible in the search bar. | P2 | PASS
TC_NB_009 | (TS_004) Navigation Bar | Validate the navbar layout is consistent and not broken | Open the Home page | 1. View the overall navbar layout and alignment (Validate ER-1) | Not Applicable | 1. All navbar items should be properly aligned with no overlapping elements. | 1. All navbar items are properly aligned in a single row with no overlapping. | P2 | PASS
TC_NB_010 | (TS_004) Navigation Bar | Validate navbar buttons have proper hover effect | Open the Home page | 1. Hover over Login, Signup, Contact, and Explore links (Validate ER-1) | Not Applicable | 1. Each element should show visible hover effect such as color change or underline. | 1. All navbar elements showed visible hover effects on mouse over. | P2 | PASS

## Explore Menu
Test Case ID | Test Scenario | Test Case Title | Pre-requisites | Test Steps | Test Data | Expected Result (ER) | Actual Result | Priority | Result | Comments
<< Test Scenarios
TC_EM_001 | (TS_005) Explore Menu | Validate Explore dropdown opens on click | Open the Home page | 1. Open the Home page 2. Click on 'Explore' in the navbar (Validate ER-1) | Not Applicable | 1. The Explore dropdown menu should open showing all 4 categories. | 1. Explore dropdown opened correctly showing all 4 categories. | P0 | PASS
TC_EM_002 | (TS_005) Explore Menu | Validate all 4 category headings are visible in the Explore dropdown | Explore dropdown is open | 1. Click Explore 2. View all category headings (Validate ER-1) | Not Applicable | 1. All 4 categories visible: IOT & SMART DEVICES, HARDWARE & ELECTRONICS, ROBOTICS & AI, EMBEDDED SYSTEMS. | 1. All 4 category headings are visible in the Explore dropdown. | P0 | PASS
TC_EM_003 | (TS_005) Explore Menu | Validate sub-items under 'IOT & SMART DEVICES' are visible | Explore dropdown open | 1. Click Explore 2. View sub-items under 'IOT & SMART DEVICES' (Validate ER-1) | Not Applicable | 1. Sub-items should show: IoT Fundamentals, Smart Home Automation, Industrial IoT, IoT Security. | 1. All sub-items under IOT & SMART DEVICES are visible as expected. | P0 | PASS
TC_EM_004 | (TS_005) Explore Menu | Validate sub-items under 'HARDWARE & ELECTRONICS' are visible | Explore dropdown open | 1. Click Explore 2. View sub-items under 'HARDWARE & ELECTRONICS' (Validate ER-1) | Not Applicable | 1. Sub-items: Arduino Programming, Raspberry Pi Projects, ESP32/ESP8266, Circuit Design. | 1. All sub-items under HARDWARE & ELECTRONICS are visible as expected. | P0 | PASS
TC_EM_005 | (TS_005) Explore Menu | Validate sub-items under 'ROBOTICS & AI' are visible | Explore dropdown open | 1. Click Explore 2. View sub-items under 'ROBOTICS & AI' (Validate ER-1) | Not Applicable | 1. Sub-items: Robotics Basics, AI for IoT, Computer Vision, Drone Programming. | 1. All sub-items under ROBOTICS & AI are visible as expected. | P0 | PASS
TC_EM_006 | (TS_005) Explore Menu | Validate sub-items under 'EMBEDDED SYSTEMS' are visible | Explore dropdown open | 1. Click Explore 2. View sub-items under 'EMBEDDED SYSTEMS' (Validate ER-1) | Not Applicable | 1. Sub-items: Embedded C Programming, RTOS Development, Microcontroller Projects, PCB Design. | 1. All sub-items under EMBEDDED SYSTEMS are visible as expected. | P0 | PASS
TC_EM_007 | (TS_005) Explore Menu | Validate Explore dropdown closes when clicking outside | Explore dropdown open | 1. Click Explore to open 2. Click anywhere outside the dropdown (Validate ER-1) | Not Applicable | 1. The Explore dropdown should close when clicking anywhere outside of it. | 1. Explore dropdown closed when clicking outside of it. | P1 | PASS
TC_EM_008 | (TS_005) Explore Menu | Validate Explore arrow icon changes on open/close | Open the Home page | 1. Note arrow icon 2. Click Explore (Validate ER-1) 3. Click again to close (Validate ER-2) | Not Applicable | 1. Arrow should point upward when open. 2. Arrow should point downward when closed. | 1. Arrow icon changed to upward on open and downward on close as expected. | P2 | PASS
TC_EM_009 | (TS_005) Explore Menu | Validate the Explore dropdown is accessible from all pages | Open the application | 1. Open /login and click Explore 2. Open /signup and click Explore 3. Open /contact and click Explore (Validate ER-1) | Not Applicable | 1. Explore dropdown should open correctly from every page. | 1. Explore dropdown opened correctly from all pages tested. | P1 | PASS
TC_EM_010 | (TS_005) Explore Menu | Validate sub-items in the Explore dropdown are clickable | Explore dropdown open | 1. Click Explore 2. Click on any sub-item link (Validate ER-1) | Not Applicable | 1. The clicked sub-item should navigate the user to the relevant page. | 1. Sub-items responded to click. Navigation was triggered on click. | P1 | PASS
TC_EM_011 | (TS_005) Explore Menu | Validate the Explore dropdown layout does not break the page | Open the Home page | 1. Click Explore 2. Observe dropdown position and page layout (Validate ER-1) | Not Applicable | 1. Dropdown should appear as an overlay without pushing page content down. | 1. Dropdown appeared as overlay. Page content was not pushed down. | P1 | PASS
TC_EM_012 | (TS_005) Explore Menu | Validate UI and alignment of the Explore dropdown | Explore dropdown open | 1. Click Explore 2. Check alignment, font, and layout (Validate ER-1) | Not Applicable | 1. Categories and sub-items should be neatly aligned in 4 columns with consistent spacing. | 1. All 4 columns are neatly aligned with consistent font and spacing. | P2 | PASS

## Search Bar
Test Case ID | Test Scenario | Test Case Title | Pre-requisites | Test Steps | Test Data | Expected Result (ER) | Actual Result | Priority | Result | Comments
<< Test Scenarios
TC_SB_001 | (TS_006) Search Bar | Validate the Search bar is visible in the navbar | Open the Home page | 1. Open the Home page 2. View the navbar (Validate ER-1) | Not Applicable | 1. Search bar should be visible with a search icon. | 1. Search bar is visible in the navbar with a search icon. | P1 | PASS
TC_SB_002 | (TS_006) Search Bar | Validate clicking the Search bar places cursor inside it | Open the Home page | 1. Click on the Search bar (Validate ER-1) | Not Applicable | 1. Cursor should appear inside the search bar when clicked. | 1. Cursor appeared inside the search bar on click. Field is focused and ready for input. | P1 | PASS
TC_SB_003 | (TS_006) Search Bar | Validate the Search bar placeholder text | Open the Home page | 1. View the Search bar without clicking (Validate ER-1) | Not Applicable | 1. Placeholder text 'Search IoT, Hardware, Projects...' should be visible. | 1. Placeholder text 'Search IoT, Hardware, Projects...' is visible. | P1 | PASS
TC_SB_004 | (TS_006) Search Bar | Validate typing a search term in the Search bar | Open the Home page | 1. Click on Search bar 2. Type 'Raspberry Pi' (Validate ER-1) | Search term: Raspberry Pi | 1. Typed text 'Raspberry Pi' should appear in the search bar. | 1. Text 'Raspberry Pi' appeared correctly in the search bar on typing. | P1 | PASS
TC_SB_005 | (TS_006) Search Bar | Validate clearing the Search bar | Search bar has text | 1. Type 'Arduino' 2. Select all and press Delete (Validate ER-1) | Search term: Arduino | 1. Search bar should become empty after deleting the text. | 1. Search bar became empty after selecting all text and pressing Delete. | P2 | PASS
TC_SB_006 | (TS_006) Search Bar | Validate the Search bar is available on all pages | Open the application | 1. Check search bar on Home, /login, /signup, /contact (Validate ER-1) | Not Applicable | 1. Search bar should be visible in the navbar on all pages. | 1. Search bar is visible in the navbar on all pages of the application. | P1 | PASS
TC_SB_007 | (TS_006) Search Bar | Validate pressing Enter key in the Search bar | Open the Home page | 1. Click Search bar 2. Type 'IoT' 3. Press Enter (Validate ER-1) | Search term: IoT | 1. Pressing Enter should trigger a search action or navigate to results page. | 1. No visible action triggered on pressing Enter. Search results page not found. | P1 | FAIL | TECHHUB-BUG-002
TC_SB_008 | (TS_006) Search Bar | Validate searching with empty input | Open the Home page | 1. Leave search bar empty 2. Press Enter or click search icon (Validate ER-1) | Not Applicable | 1. A validation message should appear or no action should be taken for empty search. | 1. No validation message shown for empty search. No feedback given to user. | P2 | FAIL | TECHHUB-BUG-003
TC_SB_009 | (TS_006) Search Bar | Validate the Search bar accepts special characters | Open the Home page | 1. Click on Search bar 2. Type '@#$%' (Validate ER-1) | Special characters: @#$% | 1. Search bar should accept the input without crashing or unexpected errors. | 1. Search bar accepted special characters without any errors or crashes. | P2 | PASS
TC_SB_010 | (TS_006) Search Bar | Validate the Search bar search icon is clickable | Open the Home page | 1. Type 'Arduino' 2. Click the search icon (Validate ER-1) | Search term: Arduino | 1. Clicking the search icon should trigger a search action. | 1. Search icon clicked but no action or result triggered. Same issue as TC_SB_007. | P1 | FAIL | TECHHUB-BUG-002

## Signup Page
Test Case ID | Test Scenario | Test Case Title | Pre-requisites | Test Steps | Test Data | Expected Result (ER) | Actual Result | Priority | Result | Comments
<< Test Scenarios
TC_SP_001 | (TS_007) Signup Page | Validate the Signup page loads correctly | Open the application | 1. Click 'Signup' in navbar (Validate ER-1) | Not Applicable | 1. Signup page should load at /signup with Full Name, Email, Password fields and Sign Up button. | 1. Signup page loaded at /signup with all fields and Sign Up button visible. | P0 | PASS
TC_SP_002 | (TS_007) Signup Page | Validate the Signup form has correct field labels and placeholders | Open the Signup page | 1. View form field labels and placeholder texts (Validate ER-1) | Not Applicable | 1. Fields: 'Full Name' - 'Enter your full name', 'Email Address' - 'Enter your email', 'Password' - 'Create a password (min 6 characters)'. | 1. All field labels and placeholder texts are displayed correctly as expected. | P0 | PASS
TC_SP_003 | (TS_007) Signup Page | Validate successful signup with all valid inputs | Open the Signup page | 1. Enter valid full name 2. Enter valid email 3. Enter password with 6+ chars 4. Click Sign Up (Validate ER-1) | Full Name: Test User Email: testuser@gmail.com Password: test@123 | 1. Signup should succeed and user should be redirected or logged in. | 1. Signup form submitted. Backend not connected so data was not persisted. Frontend action triggered. | P0 | PASS
TC_SP_004 | (TS_007) Signup Page | Validate Signup form with all fields left empty | Open the Signup page | 1. Leave all fields empty 2. Click 'Sign Up' (Validate ER-1) | Not Applicable | 1. Validation error messages should appear for all required fields. Form should not submit. | 1. No validation error messages were displayed. Form submitted without any field-level errors shown. | P0 | FAIL | TECHHUB-BUG-004
TC_SP_005 | (TS_007) Signup Page | Validate Signup with only Full Name filled | Open the Signup page | 1. Enter only Full Name 2. Leave Email and Password empty 3. Click Sign Up (Validate ER-1) | Full Name: Test User | 1. Validation errors should appear for empty Email and Password fields. | 1. No validation errors shown for empty Email and Password. Same issue as TC_SP_004. | P0 | FAIL | TECHHUB-BUG-004
TC_SP_006 | (TS_007) Signup Page | Validate Signup with an invalid email format | Open the Signup page | 1. Enter valid name 2. Enter 'testuser@' in Email 3. Enter valid password 4. Click Sign Up (Validate ER-1) | Email: testuser@ | 1. Error message: 'Please enter a valid email address'. | 1. No error message shown for invalid email format. Form proceeded without validation. | P0 | FAIL | TECHHUB-BUG-005
TC_SP_007 | (TS_007) Signup Page | Validate Signup with a password less than 6 characters | Open the Signup page | 1. Enter valid name and email 2. Enter password 'abc' 3. Click Sign Up (Validate ER-1) | Password: abc | 1. Error: 'Password must be at least 6 characters'. | 1. No error shown for short password. Form proceeded without minimum length validation. | P0 | FAIL | TECHHUB-BUG-006
TC_SP_008 | (TS_007) Signup Page | Validate Signup with only spaces in the Full Name field | Open the Signup page | 1. Enter only spaces in Full Name 2. Enter valid email and password 3. Click Sign Up (Validate ER-1) | Full Name: spaces only | 1. Validation error should be shown. Spaces only should not be accepted. | 1. No validation error shown. Spaces-only input was accepted in the Full Name field. | P1 | FAIL | TECHHUB-BUG-007
TC_SP_009 | (TS_007) Signup Page | Validate the Password field hides the entered text | Open the Signup page | 1. Click on Password field 2. Type any password (Validate ER-1) | Password: mypassword | 1. Password text should be hidden and displayed as dots or asterisks. | 1. Password text is hidden and displayed as dots as expected. | P0 | PASS
TC_SP_010 | (TS_007) Signup Page | Validate 'Already have an account? Login' link is visible and works | Open the Signup page | 1. Look for login redirect link 2. Click it (Validate ER-1, ER-2) | Not Applicable | 1. Link 'Already have an account? Login' should be visible. 2. Should navigate to /login. | 1. Link is visible below the Sign Up button. 2. Clicking it navigated to /login correctly. | P1 | PASS
TC_SP_011 | (TS_007) Signup Page | Validate Signup with a duplicate email address | An account with email already exists | 1. Enter already registered email and valid password 2. Click Sign Up (Validate ER-1) | Email: existing@gmail.com | 1. Error: 'Email already registered' or similar. | 1. No error shown for duplicate email. Backend not connected so validation not implemented. | P1 | FAIL | TECHHUB-BUG-008
TC_SP_012 | (TS_007) Signup Page | Validate the Sign Up button is visible and styled correctly | Open the Signup page | 1. View the Sign Up button (Validate ER-1) | Not Applicable | 1. Sign Up button should be visible, green colored, full width of the form. | 1. Sign Up button is visible, green colored, and spans the full width of the form. | P1 | PASS
TC_SP_013 | (TS_007) Signup Page | Validate the Signup page UI layout and alignment | Open the Signup page | 1. Review layout, font, colors and alignment (Validate ER-1) | Not Applicable | 1. Form card should be centered. All fields and buttons should be properly aligned. | 1. Form card is properly positioned. All fields and buttons are well aligned. | P2 | PASS
TC_SP_014 | (TS_007) Signup Page | Validate the browser tab title on the Signup page | Open the Signup page | 1. Open /signup 2. Check the browser tab title (Validate ER-1) | Not Applicable | 1. Browser tab should show 'TechHub - Sign Up', not 'React App'. | 1. Browser tab shows 'React App' on the Signup page. Same issue as TC_HP_009. | P3 | FAIL | TECHHUB-BUG-001
TC_SP_015 | (TS_007) Signup Page | Validate the Signup page URL is correct | Open the Signup page | 1. Click 'Signup' in navbar 2. Check the browser URL (Validate ER-1) | Not Applicable | 1. URL should be '.../signup'. | 1. URL correctly shows 'https://tech-hub-sable-two.vercel.app/signup'. | P1 | PASS
TC_SP_016 | (TS_007) Signup Page | Validate submitting Signup form using Enter key | Open the Signup page | 1. Fill all fields 2. Press Enter key (Validate ER-1) | Full Name: Test User Email: test@gmail.com Password: test@123 | 1. Form should submit on pressing Enter. | 1. Pressing Enter in the Password field submitted the form successfully. | P2 | PASS
TC_SP_017 | (TS_007) Signup Page | Validate Signup form fields accept appropriate input types | Open the Signup page | 1. Enter numbers-only in Full Name 2. Enter email without @ (Validate ER-1) | Full Name: 12345 Email: testusergmail.com | 1. Appropriate validation should trigger for wrongly formatted inputs. | 1. No validation triggered for numbers in Full Name or email without @. | P2 | FAIL | TECHHUB-BUG-005
TC_SP_018 | (TS_007) Signup Page | Validate Signup page functionality in Microsoft Edge | Open Signup page in Edge | 1. Open /signup in Edge 2. Fill valid data 3. Click Sign Up (Validate ER-1) | Full Name: Test User Email: edgetest@gmail.com Password: test@123 | 1. Signup page should function correctly in Edge. | 1. Signup page loads and functions correctly in Microsoft Edge. | P2 | PASS

## Login Page
Test Case ID | Test Scenario | Test Case Title | Pre-requisites | Test Steps | Test Data | Expected Result (ER) | Actual Result | Priority | Result | Comments
<< Test Scenarios
TC_LP_001 | (TS_008) Login Page | Validate the Login page loads correctly | Open the application | 1. Click 'Login' in navbar (Validate ER-1) | Not Applicable | 1. Login page should load at /login with Email, Password fields and Login button. | 1. Login page loaded correctly at /login with all fields and Login button visible. | P0 | PASS
TC_LP_002 | (TS_008) Login Page | Validate Login with valid credentials | A registered account exists | 1. Enter valid email 2. Enter valid password 3. Click Login (Validate ER-1) | Email: testuser@gmail.com Password: test@123 | 1. User should be logged in and redirected. | 1. Backend not connected. Login form submitted but no authentication response received. | P0 | FAIL | TECHHUB-BUG-009
TC_LP_003 | (TS_008) Login Page | Validate Login with both fields empty | Open the Login page | 1. Leave both Email and Password empty 2. Click Login (Validate ER-1) | Not Applicable | 1. Validation errors should appear for both empty fields. | 1. No validation error messages displayed for empty fields. Same issue as TC_SP_004. | P0 | FAIL | TECHHUB-BUG-004
TC_LP_004 | (TS_008) Login Page | Validate Login with invalid email and valid password | Open the Login page | 1. Enter invalid email 2. Enter valid password 3. Click Login (Validate ER-1) | Email: wronguser@gmail.com Password: test@123 | 1. Error: 'Invalid email or password'. | 1. No error message shown for invalid credentials. No backend response. | P0 | FAIL | TECHHUB-BUG-009
TC_LP_005 | (TS_008) Login Page | Validate Login with valid email and wrong password | Open the Login page | 1. Enter registered email 2. Enter wrong password 3. Click Login (Validate ER-1) | Email: testuser@gmail.com Password: wrongpass | 1. Error: 'Invalid email or password'. | 1. No error shown for wrong password. No backend validation. | P0 | FAIL | TECHHUB-BUG-009
TC_LP_006 | (TS_008) Login Page | Validate Login with invalid email format | Open the Login page | 1. Enter 'testuser@' in Email 2. Enter any password 3. Click Login (Validate ER-1) | Email: testuser@ | 1. Error: 'Please enter a valid email address'. | 1. No validation error for invalid email format in Login form. | P0 | FAIL | TECHHUB-BUG-005
TC_LP_007 | (TS_008) Login Page | Validate the Password field hides the entered text | Open the Login page | 1. Click on Password field 2. Type any password (Validate ER-1) | Password: mypassword | 1. Password text should be masked as dots or asterisks. | 1. Password text is hidden and displayed as dots as expected. | P0 | PASS
TC_LP_008 | (TS_008) Login Page | Validate Google social login button is visible | Open the Login page | 1. Open /login 2. View bottom section of login form (Validate ER-1) | Not Applicable | 1. A 'Google' login button should be visible under 'Or login with'. | 1. Google login button is visible under 'Or login with' section. | P1 | PASS
TC_LP_009 | (TS_008) Login Page | Validate GitHub social login button is visible | Open the Login page | 1. Open /login 2. View bottom section of login form (Validate ER-1) | Not Applicable | 1. A 'GitHub' login button should be visible. | 1. GitHub login button is visible under 'Or login with' section. | P1 | PASS
TC_LP_010 | (TS_008) Login Page | Validate Twitter social login button is visible | Open the Login page | 1. Open /login 2. View bottom section of login form (Validate ER-1) | Not Applicable | 1. A 'Twitter' login button should be visible. | 1. Twitter login button is visible under 'Or login with' section. | P1 | PASS
TC_LP_011 | (TS_008) Login Page | Validate 'Or login with' section label is visible | Open the Login page | 1. Look below the Login button (Validate ER-1) | Not Applicable | 1. Text 'Or login with' should be visible as separator above social login buttons. | 1. 'Or login with' text is visible as a separator above the social login buttons. | P1 | PASS
TC_LP_012 | (TS_008) Login Page | Validate 'Don't have an account? Sign up' link works | Open the Login page | 1. Look for signup redirect link 2. Click it (Validate ER-1, ER-2) | Not Applicable | 1. Link should be visible. 2. Should navigate to /signup. | 1. Link is visible. 2. Clicking 'Sign up' navigated to /signup correctly. | P1 | PASS
TC_LP_013 | (TS_008) Login Page | Validate the Login page URL is correct | Open the Login page | 1. Click Login in navbar 2. Check browser URL (Validate ER-1) | Not Applicable | 1. URL should be '.../login'. | 1. URL correctly shows 'https://tech-hub-sable-two.vercel.app/login'. | P1 | PASS
TC_LP_014 | (TS_008) Login Page | Validate the browser tab title on the Login page | Open the Login page | 1. Open /login 2. Check browser tab title (Validate ER-1) | Not Applicable | 1. Tab should show 'TechHub - Login', not 'React App'. | 1. Browser tab shows 'React App' on Login page. Same issue as TC_HP_009. | P3 | FAIL | TECHHUB-BUG-001
TC_LP_015 | (TS_008) Login Page | Validate Login page form field placeholders | Open the Login page | 1. View placeholder texts inside Email and Password fields (Validate ER-1) | Not Applicable | 1. Email: 'Enter your email'. Password: 'Enter your password'. | 1. Both fields display correct placeholder texts as expected. | P1 | PASS
TC_LP_016 | (TS_008) Login Page | Validate the Login page UI layout and alignment | Open the Login page | 1. Review layout, font, colors, and alignment (Validate ER-1) | Not Applicable | 1. Form card should be properly positioned. All elements well aligned. | 1. Form card is properly positioned. All fields, buttons, and text are well aligned. | P2 | PASS

## Social Login
Test Case ID | Test Scenario | Test Case Title | Pre-requisites | Test Steps | Test Data | Expected Result (ER) | Actual Result | Priority | Result | Comments
<< Test Scenarios
TC_SL_001 | (TS_009) Social Login | Validate all three social login buttons are visible | Open the Login page | 1. Open /login 2. View bottom of login form (Validate ER-1) | Not Applicable | 1. Three buttons should be visible: Google, GitHub, and Twitter. | 1. All three social login buttons are visible: Google, GitHub, and Twitter. | P1 | PASS
TC_SL_002 | (TS_009) Social Login | Validate Google login button is clickable | Open the Login page | 1. Open /login 2. Click the Google login button (Validate ER-1) | Not Applicable | 1. Should initiate Google OAuth flow or show relevant response. | 1. Google button is clickable but OAuth not configured. No authentication flow triggered. | P1 | FAIL | TECHHUB-BUG-010
TC_SL_003 | (TS_009) Social Login | Validate GitHub login button is clickable | Open the Login page | 1. Open /login 2. Click the GitHub login button (Validate ER-1) | Not Applicable | 1. Should initiate GitHub OAuth flow or show relevant response. | 1. GitHub button is clickable but OAuth not configured. No authentication flow triggered. | P1 | FAIL | TECHHUB-BUG-010
TC_SL_004 | (TS_009) Social Login | Validate Twitter login button is clickable | Open the Login page | 1. Open /login 2. Click the Twitter login button (Validate ER-1) | Not Applicable | 1. Should initiate Twitter OAuth flow or show relevant response. | 1. Twitter button is clickable but OAuth not configured. No authentication flow triggered. | P1 | FAIL | TECHHUB-BUG-010
TC_SL_005 | (TS_009) Social Login | Validate social login buttons have hover effect | Open the Login page | 1. Hover over each social login button (Validate ER-1) | Not Applicable | 1. Each button should show visual hover effect. | 1. All three buttons showed visual hover effects on mouse over. | P2 | PASS
TC_SL_006 | (TS_009) Social Login | Validate social login buttons display correct labels | Open the Login page | 1. View labels on each social login button (Validate ER-1) | Not Applicable | 1. Buttons should be labelled 'Google', 'GitHub', and 'Twitter'. | 1. All three buttons are correctly labelled 'Google', 'GitHub', and 'Twitter'. | P1 | PASS

## Contact Page
Test Case ID | Test Scenario | Test Case Title | Pre-requisites | Test Steps | Test Data | Expected Result (ER) | Actual Result | Priority | Result | Comments
<< Test Scenarios
TC_CP_001 | (TS_010) Contact Page | Validate the Contact page loads correctly | Open the application | 1. Click 'Contact' in navbar (Validate ER-1) | Not Applicable | 1. Contact page should load at /contact with 'Get In Touch' heading and 4 info cards. | 1. Contact page loaded at /contact with 'Get In Touch' heading and all 4 info cards visible. | P2 | PASS
TC_CP_002 | (TS_010) Contact Page | Validate the 'Get In Touch' heading is visible | Open the Contact page | 1. Open /contact 2. View the top section (Validate ER-1) | Not Applicable | 1. Heading 'Get In Touch' should be clearly visible at top of page. | 1. 'Get In Touch' heading is clearly visible at the top of the Contact page. | P2 | PASS
TC_CP_003 | (TS_010) Contact Page | Validate the description text below heading is visible | Open the Contact page | 1. View text below 'Get In Touch' (Validate ER-1) | Not Applicable | 1. Description text should be visible and readable. | 1. Description text is visible and readable below the heading. | P2 | PASS
TC_CP_004 | (TS_010) Contact Page | Validate all 4 contact info cards are visible | Open the Contact page | 1. View the 4 cards section (Validate ER-1) | Not Applicable | 1. Four cards should be visible: Phone, Email, Location, Working Hours. | 1. All four cards are visible: Phone, Email, Location, and Working Hours. | P2 | PASS
TC_CP_005 | (TS_010) Contact Page | Validate the Phone card displays phone numbers correctly | Open the Contact page | 1. View the Phone card (Validate ER-1) | Not Applicable | 1. Phone card should display phone icon and two phone numbers. | 1. Phone card displays the phone icon and two phone number entries correctly. | P2 | PASS
TC_CP_006 | (TS_010) Contact Page | Validate the Email card displays email addresses correctly | Open the Contact page | 1. View the Email card (Validate ER-1) | Not Applicable | 1. Email card should display email icon and two email addresses. | 1. Email card displays email icon and two email addresses correctly. | P2 | PASS
TC_CP_007 | (TS_010) Contact Page | Validate the Location card displays address correctly | Open the Contact page | 1. View the Location card (Validate ER-1) | Not Applicable | 1. Location card should display location icon and full address. | 1. Location card displays the location icon and full address correctly. | P3 | PASS
TC_CP_008 | (TS_010) Contact Page | Validate the Working Hours card displays hours correctly | Open the Contact page | 1. View the Working Hours card (Validate ER-1) | Not Applicable | 1. Working Hours card should display clock icon, weekday hours, and weekend status. | 1. Working Hours card displays clock icon, Mon-Fri hours, and Sat-Sun: Closed correctly. | P3 | PASS

## Page Navigation
Test Case ID | Test Scenario | Test Case Title | Pre-requisites | Test Steps | Test Data | Expected Result (ER) | Actual Result | Priority | Result | Comments
<< Test Scenarios
TC_PN_001 | (TS_011) Page Navigation | Validate navigating from Home to Login page | Open the Home page | 1. Click 'Login' in navbar (Validate ER-1) | Not Applicable | 1. User should navigate to Login page at /login. | 1. User navigated to Login page at /login successfully. | P0 | PASS
TC_PN_002 | (TS_011) Page Navigation | Validate navigating from Home to Signup page | Open the Home page | 1. Click 'Signup' in navbar (Validate ER-1) | Not Applicable | 1. User should navigate to Signup page at /signup. | 1. User navigated to Signup page at /signup successfully. | P0 | PASS
TC_PN_003 | (TS_011) Page Navigation | Validate navigating from Home to Contact page | Open the Home page | 1. Click 'Contact' in navbar (Validate ER-1) | Not Applicable | 1. User should navigate to Contact page at /contact. | 1. User navigated to Contact page at /contact successfully. | P1 | PASS
TC_PN_004 | (TS_011) Page Navigation | Validate navigating from Login back to Home via logo | Open the Login page | 1. Click TechHub logo in navbar (Validate ER-1) | Not Applicable | 1. User should navigate back to Home page. | 1. Clicking the logo navigated back to the Home page correctly. | P1 | PASS
TC_PN_005 | (TS_011) Page Navigation | Validate navigating from Signup to Login using the link | Open the Signup page | 1. Click 'Already have an account? Login' link (Validate ER-1) | Not Applicable | 1. User should navigate to Login page at /login. | 1. User navigated to /login via the link correctly. | P1 | PASS
TC_PN_006 | (TS_011) Page Navigation | Validate navigating from Login to Signup using the link | Open the Login page | 1. Click 'Don't have an account? Sign up' link (Validate ER-1) | Not Applicable | 1. User should navigate to Signup page at /signup. | 1. User navigated to /signup via the link correctly. | P1 | PASS
TC_PN_007 | (TS_011) Page Navigation | Validate using browser back button after navigation | On Login page, came from Home | 1. Go to Home 2. Click Login 3. Press browser back button (Validate ER-1) | Not Applicable | 1. User should be taken back to the Home page. | 1. Browser back button navigated back to the Home page correctly. | P1 | PASS
TC_PN_008 | (TS_011) Page Navigation | Validate direct URL access for all pages | Open a browser | 1. Type /login in URL (Validate ER-1) 2. Type /signup (Validate ER-2) 3. Type /contact (Validate ER-3) | Not Applicable | 1. /login loads Login page. 2. /signup loads Signup page. 3. /contact loads Contact page. | 1. All three pages loaded correctly when accessed directly via URL. | P0 | PASS

## UI Consistency
Test Case ID | Test Scenario | Test Case Title | Pre-requisites | Test Steps | Test Data | Expected Result (ER) | Actual Result | Priority | Result | Comments
<< Test Scenarios
TC_UI_001 | (TS_012) UI Consistency | Validate green color theme is consistent across all pages | Open the application | 1. Visit all pages 2. Check navbar and button colors (Validate ER-1) | Not Applicable | 1. Green color theme should be consistent on all pages. | 1. Green color theme is consistent across all pages. | P2 | PASS
TC_UI_002 | (TS_012) UI Consistency | Validate font style is consistent across all pages | Open the application | 1. Visit all pages 2. Check font style and size (Validate ER-1) | Not Applicable | 1. Same font family and consistent sizing across all pages. | 1. Font family and sizing are consistent across all pages. | P2 | PASS
TC_UI_003 | (TS_012) UI Consistency | Validate navbar appearance is identical across all pages | Open the application | 1. Visit all pages 2. Compare the navbar on each page (Validate ER-1) | Not Applicable | 1. Navbar should look identical on all pages. | 1. Navbar appears identical across all pages - same logo, links, search bar, and buttons. | P2 | PASS
TC_UI_004 | (TS_012) UI Consistency | Validate no text is cut off or overflowing outside its container | Open the application | 1. Inspect all text blocks on all pages (Validate ER-1) | Not Applicable | 1. No text should overflow outside its container. | 1. No text overflow observed on any page. All text is fully readable. | P2 | PASS
TC_UI_005 | (TS_012) UI Consistency | Validate no broken images appear on any page | Open the application | 1. Check all images on all pages (Validate ER-1) | Not Applicable | 1. No broken image icons should appear on any page. | 1. No broken image icons observed. All images load completely. | P1 | PASS
TC_UI_006 | (TS_012) UI Consistency | Validate all clickable elements have a pointer cursor on hover | Open the application | 1. Hover over all buttons and links on all pages (Validate ER-1) | Not Applicable | 1. All buttons and links should display a pointer cursor on hover. | 1. All buttons and links display pointer cursor on hover as expected. | P2 | PASS
TC_UI_007 | (TS_012) UI Consistency | Validate the browser tab title across all pages | Open the application | 1. Open each page and check browser tab title (Validate ER-1) | Not Applicable | 1. Each page should have its own descriptive title. None should say 'React App'. | 1. All pages show 'React App' in the browser tab. No page-specific titles set. | P3 | FAIL | TECHHUB-BUG-001
TC_UI_008 | (TS_012) UI Consistency | Validate page layout does not break at 125% browser zoom | Open Chrome | 1. Open Home page 2. Zoom to 125% 3. Check all pages (Validate ER-1) | Browser zoom: 125% | 1. All pages should remain readable and layout should not break at 125% zoom. | 1. Minor overlap observed in the navbar at 125% zoom. Items slightly crowded but readable. | P2 | FAIL | TECHHUB-BUG-011